## Plan
Software insallation | VS 2019 community edition | .Net Core | Azure DevOps
| .net core SDK 3.1 | WebAPI | Azure SQL DB
| SQL Server community edition | EF Core | Azure AD
| github, gitbash | LINQ | Key Vault
| postman, Jmeter | SQL Server | App Services
| Notepad ++ | Postman | WebApps
| windows powershell ISE | Swagger | WebJobs
|  | Jmeter | App Insights
git hub account | create account | SonarQube | Storage account
| clone repo to local machine | Jira, agile
github
Azure subscription | create account, subscription, resource group, Azure AD tenant | xUnit
| create app service, key vault |  | ServiceBus
Az Functions
1 | create vs .net core 3.1 project for webapi
enable swagger documentation
Test the localhost URL using swagger, postman
create a feature branch
push changes to git
deploy manually to azure
Test the azure URL using swagger, postman, Jmeter
2 | create sql server in Azure, database, schema
create sample data, indexes
3 | create azure secrets for DB connection string
Integrate keyvault with .net core
register application with azure AD
deploy & test keyvault secrets
4 | create multiple libraries for Interfaces, Data, Service layer
create entity framework db context from sql server schema
modify startup.cs file for dbcontext and keyvault connection string
Implement basic CRUD operations on one table
Automapper
test APIs locally in swagger, postman
deploy manually to azure
Test the azure URL using swagger, postman, Jmeter
5 | create devops build & release pipelines from master branch
raise a PR to master branch
Test the azure URL using swagger, postman, Jmeter
6 | xUnit integration
7 | sonarQube integration
8 | AppInsights integration
Custom exception handler
9 | Create Azure AD users
Implement APIs with RBAC
10 | Create mutiple user types in database table
create users from .net API
create JWT token using API
Implement APIs with PBAC
11 | Update DevOps CI with xUnit, SonarQube
Implement Approvals, Gates
12 | Repository pattern
Dependeny Injection
13 | Expression Builder for criteria
Pagination
14 | Query optimization using BenchmarkDotnet
ToList, ToListAsync()
Outer joins

## Progress
2022-11-24 | Topics | Discussed about Software installation |  | vs2019
|  | Created new .Net core web api project |  | sql server (ssms)
|  | Weatherforecast controller is created automatically with the template |  | github
|  | NuGet package manager -> installed swashbuckle 2 packages Aspnetcore, annotations |  | gitbash
|  | Written the swagger coding in startup.cs file |  | postman
|  | Tested the weatherforecast in swagger URL |  | jmeter
|  | Added HomeController with GET, POST basic methods |  | .net sdk 3.1 - 6.0
|  | Tested the home controller APIs in swagger URL |  | notepad++, winzip, acrobat, IBM open office
Tested both the controller APIs in postman
Created collection using swagger json file
Studied variables created automatically in postman
Added EmployeDTO class in the .net Models folder
Created GET, POST APIs with EmployeeDTO as request, response params
|  | Discussed about project explanation |  | Slide in the PPT
|  | Discussed about git branching strategies |  | Slide in the PPT
|  | Discussed about API versioning concepts |  | https://productname.mycompany.com/api/v1/Home/save-employee?id=45
| Notes | GET, POST, PUT, DELETE HTTP VERBS |  | https://productname.mycompany.com/api/v2/Home/save-employee?name=srikanth
HTTP, HTTPS, SSL, TLS
MVC Controller, API controller
Startup.cs
HTTP Status codes
Web Host Builder Class
Conventional, Attribute routing
2022-11-25
2022-11-27
| Login | Login to github account
Create a repository
github branches are case sensitive
| Create a new local folder | Connect one folder from your local machine to this repo using bash commands
Push the changes to repo master brach
change the default branch to master in github
you need to remove .git folder and entire folder structure in local machine
to avoid the error remote: permission to chapter2.git denied to mkvaddiparthi fatal: unable to access 'https://github.com/muraliguru2016/chapter2.git'
follow the below step 1) Windows credentials manager -> windows credentials -> generic credentials 2) delete github.com user
Local folder contains the solution
git init git add -A git commit -m "first commit" git branch -M main git remote add origin https://github.com/muraligit2000/ChapterPart9.git git push -f origin main
Pull from vs2019. push changes to master branch
Create a feature branch from master
Pull the feature branch from vs2019. back merge.
Stashes
Push changes
Merge the PR
Multiple commits and single PR
View history
git ignore
|  | Protect the master branch from direct pushes |  | file1 - 522
Create another user in git
Invite second user for PR merges
| git Terminology | centralized, distributed version controlling systems
|  | svn, apache subversion, perforce, TFS, CVS | file1 (522) |  | file3 (505)
github, bitbucket
|  | repository, projects, branches, local, remote |  | file2 (520)
checkout, checkin
pull, back merge, commit, push, PR, approve, merge
git bash commnds
conflicts, stashing, view history, cherry pick
squash merge
labelling, rebase, revert
Personal access tokens
2022-11-28